## Sheet1
| Activity | SourceObject | start_time | state | duration | end_time | cp_activity_id
0 | basic activity:barge_0 | barge_0 | 1970-01-01 | ACTIVE | 0.023148 | 1970-01-01 00:33 | cp_activity_3
1 | basic activity:barge_1 | barge_1 | 1970-01-01 | ACTIVE | 0.023148 | 1970-01-01 00:33 | cp_activity_13
2 | basic activity vessel_last | vessel_last | 1970-01-01 | WAITING | 1.2442 | 1970-01-02 05:52 | cp_activity_1
3 | sailing empty:barge_0 | barge_0 | 1970-01-01 00:33 | ACTIVE | 0.023148 | 1970-01-01 01:07 | cp_activity_45
4 | sailing empty:barge_1 | barge_1 | 1970-01-01 00:33 | ACTIVE | 0.023148 | 1970-01-01 01:07 | cp_activity_55
5 | loading:barge_0 | barge_0 | 1970-01-01 01:07 | ACTIVE | 0.028935 | 1970-01-01 01:48 | cp_activity_24
6 | loading:barge_0 | from_site | 1970-01-01 01:07 | ACTIVE | 0.028935 | 1970-01-01 01:48 | cp_activity_24
7 | loading:barge_1 | from_site | 1970-01-01 01:48 | ACTIVE | 0.028935 | 1970-01-01 02:30 | cp_activity_34
8 | loading:barge_1 | barge_1 | 1970-01-01 01:48 | ACTIVE | 0.028935 | 1970-01-01 02:30 | cp_activity_34
9 | sailing full:barge_0 | barge_0 | 1970-01-01 01:48 | ACTIVE | 0.023148 | 1970-01-01 02:22 | cp_activity_66
10 | unloading:barge_0 | to_site | 1970-01-01 02:22 | ACTIVE | 0.023148 | 1970-01-01 02:55 | cp_activity_87
11 | unloading:barge_0 | barge_0 | 1970-01-01 02:22 | ACTIVE | 0.023148 | 1970-01-01 02:55 | cp_activity_87
12 | sailing full:barge_1 | barge_1 | 1970-01-01 02:30 | ACTIVE | 0.023148 | 1970-01-01 03:03 | cp_activity_76
13 | basic activity:barge_0 | barge_0 | 1970-01-01 02:55 | ACTIVE | 0.023148 | 1970-01-01 03:28 | cp_activity_4
14 | unloading:barge_1 | barge_1 | 1970-01-01 03:03 | ACTIVE | 0.023148 | 1970-01-01 03:37 | cp_activity_97
15 | unloading:barge_1 | to_site | 1970-01-01 03:03 | ACTIVE | 0.023148 | 1970-01-01 03:37 | cp_activity_97
16 | sailing empty:barge_0 | barge_0 | 1970-01-01 03:28 | ACTIVE | 0.023148 | 1970-01-01 04:02 | cp_activity_46
17 | basic activity:barge_1 | barge_1 | 1970-01-01 03:37 | ACTIVE | 0.023148 | 1970-01-01 04:10 | cp_activity_14
18 | loading:barge_0 | barge_0 | 1970-01-01 04:02 | ACTIVE | 0.028935 | 1970-01-01 04:43 | cp_activity_25
19 | loading:barge_0 | from_site | 1970-01-01 04:02 | ACTIVE | 0.028935 | 1970-01-01 04:43 | cp_activity_25
20 | sailing empty:barge_1 | barge_1 | 1970-01-01 04:10 | ACTIVE | 0.023148 | 1970-01-01 04:43 | cp_activity_56
21 | loading:barge_1 | from_site | 1970-01-01 04:43 | ACTIVE | 0.028935 | 1970-01-01 05:25 | cp_activity_35
22 | sailing full:barge_0 | barge_0 | 1970-01-01 04:43 | ACTIVE | 0.023148 | 1970-01-01 05:17 | cp_activity_67
23 | loading:barge_1 | barge_1 | 1970-01-01 04:43 | ACTIVE | 0.028935 | 1970-01-01 05:25 | cp_activity_35
24 | unloading:barge_0 | barge_0 | 1970-01-01 05:17 | ACTIVE | 0.023148 | 1970-01-01 05:50 | cp_activity_88
25 | unloading:barge_0 | to_site | 1970-01-01 05:17 | ACTIVE | 0.023148 | 1970-01-01 05:50 | cp_activity_88
26 | sailing full:barge_1 | barge_1 | 1970-01-01 05:25 | ACTIVE | 0.023148 | 1970-01-01 05:58 | cp_activity_77
27 | basic activity:barge_0 | barge_0 | 1970-01-01 05:50 | ACTIVE | 0.023148 | 1970-01-01 06:23 | cp_activity_5
28 | unloading:barge_1 | to_site | 1970-01-01 05:58 | ACTIVE | 0.023148 | 1970-01-01 06:32 | cp_activity_98
29 | unloading:barge_1 | barge_1 | 1970-01-01 05:58 | ACTIVE | 0.023148 | 1970-01-01 06:32 | cp_activity_98
30 | sailing empty:barge_0 | barge_0 | 1970-01-01 06:23 | ACTIVE | 0.023148 | 1970-01-01 06:57 | cp_activity_47
31 | basic activity:barge_1 | barge_1 | 1970-01-01 06:32 | ACTIVE | 0.023148 | 1970-01-01 07:05 | cp_activity_15
32 | loading:barge_0 | barge_0 | 1970-01-01 06:57 | ACTIVE | 0.028935 | 1970-01-01 07:38 | cp_activity_26
33 | loading:barge_0 | from_site | 1970-01-01 06:57 | ACTIVE | 0.028935 | 1970-01-01 07:38 | cp_activity_26
34 | sailing empty:barge_1 | barge_1 | 1970-01-01 07:05 | ACTIVE | 0.023148 | 1970-01-01 07:38 | cp_activity_57
35 | loading:barge_1 | from_site | 1970-01-01 07:38 | ACTIVE | 0.028935 | 1970-01-01 08:20 | cp_activity_36
36 | loading:barge_1 | barge_1 | 1970-01-01 07:38 | ACTIVE | 0.028935 | 1970-01-01 08:20 | cp_activity_36
37 | sailing full:barge_0 | barge_0 | 1970-01-01 07:38 | ACTIVE | 0.023148 | 1970-01-01 08:12 | cp_activity_68
38 | unloading:barge_0 | barge_0 | 1970-01-01 08:12 | ACTIVE | 0.023148 | 1970-01-01 08:45 | cp_activity_89
39 | unloading:barge_0 | to_site | 1970-01-01 08:12 | ACTIVE | 0.023148 | 1970-01-01 08:45 | cp_activity_89
40 | sailing full:barge_1 | barge_1 | 1970-01-01 08:20 | ACTIVE | 0.023148 | 1970-01-01 08:53 | cp_activity_78
41 | basic activity:barge_0 | barge_0 | 1970-01-01 08:45 | ACTIVE | 0.023148 | 1970-01-01 09:18 | cp_activity_6
42 | unloading:barge_1 | to_site | 1970-01-01 08:53 | ACTIVE | 0.023148 | 1970-01-01 09:27 | cp_activity_99
43 | unloading:barge_1 | barge_1 | 1970-01-01 08:53 | ACTIVE | 0.023148 | 1970-01-01 09:27 | cp_activity_99
44 | sailing empty:barge_0 | barge_0 | 1970-01-01 09:18 | ACTIVE | 0.023148 | 1970-01-01 09:52 | cp_activity_48
45 | basic activity:barge_1 | barge_1 | 1970-01-01 09:27 | ACTIVE | 0.023148 | 1970-01-01 10:00 | cp_activity_16
46 | loading:barge_0 | from_site | 1970-01-01 09:52 | ACTIVE | 0.028935 | 1970-01-01 10:33 | cp_activity_27
47 | loading:barge_0 | barge_0 | 1970-01-01 09:52 | ACTIVE | 0.028935 | 1970-01-01 10:33 | cp_activity_27
48 | sailing empty:barge_1 | barge_1 | 1970-01-01 10:00 | ACTIVE | 0.023148 | 1970-01-01 10:33 | cp_activity_58
49 | loading:barge_1 | from_site | 1970-01-01 10:33 | ACTIVE | 0.028935 | 1970-01-01 11:15 | cp_activity_37
50 | sailing full:barge_0 | barge_0 | 1970-01-01 10:33 | ACTIVE | 0.023148 | 1970-01-01 11:07 | cp_activity_69
51 | loading:barge_1 | barge_1 | 1970-01-01 10:33 | ACTIVE | 0.028935 | 1970-01-01 11:15 | cp_activity_37
52 | unloading:barge_0 | barge_0 | 1970-01-01 11:07 | ACTIVE | 0.023148 | 1970-01-01 11:40 | cp_activity_90
53 | unloading:barge_0 | to_site | 1970-01-01 11:07 | ACTIVE | 0.023148 | 1970-01-01 11:40 | cp_activity_90
54 | sailing full:barge_1 | barge_1 | 1970-01-01 11:15 | ACTIVE | 0.023148 | 1970-01-01 11:48 | cp_activity_79
55 | basic activity:barge_0 | barge_0 | 1970-01-01 11:40 | ACTIVE | 0.023148 | 1970-01-01 12:13 | cp_activity_7
56 | unloading:barge_1 | barge_1 | 1970-01-01 11:48 | ACTIVE | 0.023148 | 1970-01-01 12:22 | cp_activity_100
57 | unloading:barge_1 | to_site | 1970-01-01 11:48 | ACTIVE | 0.023148 | 1970-01-01 12:22 | cp_activity_100
58 | sailing empty:barge_0 | barge_0 | 1970-01-01 12:13 | ACTIVE | 0.023148 | 1970-01-01 12:47 | cp_activity_49
59 | basic activity:barge_1 | barge_1 | 1970-01-01 12:22 | ACTIVE | 0.023148 | 1970-01-01 12:55 | cp_activity_17
60 | loading:barge_0 | from_site | 1970-01-01 12:47 | ACTIVE | 0.028935 | 1970-01-01 13:28 | cp_activity_28
61 | loading:barge_0 | barge_0 | 1970-01-01 12:47 | ACTIVE | 0.028935 | 1970-01-01 13:28 | cp_activity_28
62 | sailing empty:barge_1 | barge_1 | 1970-01-01 12:55 | ACTIVE | 0.023148 | 1970-01-01 13:28 | cp_activity_59
63 | loading:barge_1 | barge_1 | 1970-01-01 13:28 | ACTIVE | 0.028935 | 1970-01-01 14:10 | cp_activity_38
64 | loading:barge_1 | from_site | 1970-01-01 13:28 | ACTIVE | 0.028935 | 1970-01-01 14:10 | cp_activity_38
65 | sailing full:barge_0 | barge_0 | 1970-01-01 13:28 | ACTIVE | 0.023148 | 1970-01-01 14:02 | cp_activity_70
66 | unloading:barge_0 | barge_0 | 1970-01-01 14:02 | ACTIVE | 0.023148 | 1970-01-01 14:35 | cp_activity_91
67 | unloading:barge_0 | to_site | 1970-01-01 14:02 | ACTIVE | 0.023148 | 1970-01-01 14:35 | cp_activity_91
68 | sailing full:barge_1 | barge_1 | 1970-01-01 14:10 | ACTIVE | 0.023148 | 1970-01-01 14:43 | cp_activity_80
69 | basic activity:barge_0 | barge_0 | 1970-01-01 14:35 | ACTIVE | 0.023148 | 1970-01-01 15:08 | cp_activity_8
70 | unloading:barge_1 | barge_1 | 1970-01-01 14:43 | ACTIVE | 0.023148 | 1970-01-01 15:17 | cp_activity_101
71 | unloading:barge_1 | to_site | 1970-01-01 14:43 | ACTIVE | 0.023148 | 1970-01-01 15:17 | cp_activity_101
72 | sailing empty:barge_0 | barge_0 | 1970-01-01 15:08 | ACTIVE | 0.023148 | 1970-01-01 15:42 | cp_activity_50
73 | basic activity:barge_1 | barge_1 | 1970-01-01 15:17 | ACTIVE | 0.023148 | 1970-01-01 15:50 | cp_activity_18
74 | loading:barge_0 | from_site | 1970-01-01 15:42 | ACTIVE | 0.028935 | 1970-01-01 16:23 | cp_activity_29
75 | loading:barge_0 | barge_0 | 1970-01-01 15:42 | ACTIVE | 0.028935 | 1970-01-01 16:23 | cp_activity_29
76 | sailing empty:barge_1 | barge_1 | 1970-01-01 15:50 | ACTIVE | 0.023148 | 1970-01-01 16:23 | cp_activity_60
77 | loading:barge_1 | from_site | 1970-01-01 16:23 | ACTIVE | 0.028935 | 1970-01-01 17:05 | cp_activity_39
78 | loading:barge_1 | barge_1 | 1970-01-01 16:23 | ACTIVE | 0.028935 | 1970-01-01 17:05 | cp_activity_39
79 | sailing full:barge_0 | barge_0 | 1970-01-01 16:23 | ACTIVE | 0.023148 | 1970-01-01 16:57 | cp_activity_71
80 | unloading:barge_0 | barge_0 | 1970-01-01 16:57 | ACTIVE | 0.023148 | 1970-01-01 17:30 | cp_activity_92
81 | unloading:barge_0 | to_site | 1970-01-01 16:57 | ACTIVE | 0.023148 | 1970-01-01 17:30 | cp_activity_92
82 | sailing full:barge_1 | barge_1 | 1970-01-01 17:05 | ACTIVE | 0.023148 | 1970-01-01 17:38 | cp_activity_81
83 | basic activity:barge_0 | barge_0 | 1970-01-01 17:30 | ACTIVE | 0.023148 | 1970-01-01 18:03 | cp_activity_9
84 | unloading:barge_1 | to_site | 1970-01-01 17:38 | ACTIVE | 0.023148 | 1970-01-01 18:12 | cp_activity_102
85 | unloading:barge_1 | barge_1 | 1970-01-01 17:38 | ACTIVE | 0.023148 | 1970-01-01 18:12 | cp_activity_102
86 | sailing empty:barge_0 | barge_0 | 1970-01-01 18:03 | ACTIVE | 0.023148 | 1970-01-01 18:37 | cp_activity_51
87 | basic activity:barge_1 | barge_1 | 1970-01-01 18:12 | ACTIVE | 0.023148 | 1970-01-01 18:45 | cp_activity_19
88 | loading:barge_0 | from_site | 1970-01-01 18:37 | ACTIVE | 0.028935 | 1970-01-01 19:18 | cp_activity_30
89 | loading:barge_0 | barge_0 | 1970-01-01 18:37 | ACTIVE | 0.028935 | 1970-01-01 19:18 | cp_activity_30
90 | sailing empty:barge_1 | barge_1 | 1970-01-01 18:45 | ACTIVE | 0.023148 | 1970-01-01 19:18 | cp_activity_61
91 | loading:barge_1 | barge_1 | 1970-01-01 19:18 | ACTIVE | 0.028935 | 1970-01-01 20:00 | cp_activity_40
92 | loading:barge_1 | from_site | 1970-01-01 19:18 | ACTIVE | 0.028935 | 1970-01-01 20:00 | cp_activity_40
93 | sailing full:barge_0 | barge_0 | 1970-01-01 19:18 | ACTIVE | 0.023148 | 1970-01-01 19:52 | cp_activity_72
94 | unloading:barge_0 | to_site | 1970-01-01 19:52 | ACTIVE | 0.023148 | 1970-01-01 20:25 | cp_activity_93
95 | unloading:barge_0 | barge_0 | 1970-01-01 19:52 | ACTIVE | 0.023148 | 1970-01-01 20:25 | cp_activity_93
96 | sailing full:barge_1 | barge_1 | 1970-01-01 20:00 | ACTIVE | 0.023148 | 1970-01-01 20:33 | cp_activity_82
97 | basic activity:barge_0 | barge_0 | 1970-01-01 20:25 | ACTIVE | 0.023148 | 1970-01-01 20:58 | cp_activity_10
98 | unloading:barge_1 | to_site | 1970-01-01 20:33 | ACTIVE | 0.023148 | 1970-01-01 21:07 | cp_activity_103
99 | unloading:barge_1 | barge_1 | 1970-01-01 20:33 | ACTIVE | 0.023148 | 1970-01-01 21:07 | cp_activity_103
100 | sailing empty:barge_0 | barge_0 | 1970-01-01 20:58 | ACTIVE | 0.023148 | 1970-01-01 21:32 | cp_activity_52
101 | basic activity:barge_1 | barge_1 | 1970-01-01 21:07 | ACTIVE | 0.023148 | 1970-01-01 21:40 | cp_activity_20
102 | loading:barge_0 | barge_0 | 1970-01-01 21:32 | ACTIVE | 0.028935 | 1970-01-01 22:13 | cp_activity_31
103 | loading:barge_0 | from_site | 1970-01-01 21:32 | ACTIVE | 0.028935 | 1970-01-01 22:13 | cp_activity_31
104 | sailing empty:barge_1 | barge_1 | 1970-01-01 21:40 | ACTIVE | 0.023148 | 1970-01-01 22:13 | cp_activity_62
105 | loading:barge_1 | from_site | 1970-01-01 22:13 | ACTIVE | 0.028935 | 1970-01-01 22:55 | cp_activity_41
106 | sailing full:barge_0 | barge_0 | 1970-01-01 22:13 | ACTIVE | 0.023148 | 1970-01-01 22:47 | cp_activity_73
107 | loading:barge_1 | barge_1 | 1970-01-01 22:13 | ACTIVE | 0.028935 | 1970-01-01 22:55 | cp_activity_41
108 | unloading:barge_0 | to_site | 1970-01-01 22:47 | ACTIVE | 0.023148 | 1970-01-01 23:20 | cp_activity_94
109 | unloading:barge_0 | barge_0 | 1970-01-01 22:47 | ACTIVE | 0.023148 | 1970-01-01 23:20 | cp_activity_94
110 | sailing full:barge_1 | barge_1 | 1970-01-01 22:55 | ACTIVE | 0.023148 | 1970-01-01 23:28 | cp_activity_83
111 | basic activity:barge_0 | barge_0 | 1970-01-01 23:20 | ACTIVE | 0.023148 | 1970-01-01 23:53 | cp_activity_11
112 | unloading:barge_1 | to_site | 1970-01-01 23:28 | ACTIVE | 0.023148 | 1970-01-02 00:02 | cp_activity_104
113 | unloading:barge_1 | barge_1 | 1970-01-01 23:28 | ACTIVE | 0.023148 | 1970-01-02 00:02 | cp_activity_104
114 | sailing empty:barge_0 | barge_0 | 1970-01-01 23:53 | ACTIVE | 0.023148 | 1970-01-02 00:27 | cp_activity_53
115 | basic activity:barge_1 | barge_1 | 1970-01-02 00:02 | ACTIVE | 0.023148 | 1970-01-02 00:35 | cp_activity_21
116 | loading:barge_0 | from_site | 1970-01-02 00:27 | ACTIVE | 0.028935 | 1970-01-02 01:08 | cp_activity_32
117 | loading:barge_0 | barge_0 | 1970-01-02 00:27 | ACTIVE | 0.028935 | 1970-01-02 01:08 | cp_activity_32
118 | sailing empty:barge_1 | barge_1 | 1970-01-02 00:35 | ACTIVE | 0.023148 | 1970-01-02 01:08 | cp_activity_63
119 | sailing full:barge_0 | barge_0 | 1970-01-02 01:08 | ACTIVE | 0.023148 | 1970-01-02 01:42 | cp_activity_74
120 | loading:barge_1 | from_site | 1970-01-02 01:08 | ACTIVE | 0.028935 | 1970-01-02 01:50 | cp_activity_42
121 | loading:barge_1 | barge_1 | 1970-01-02 01:08 | ACTIVE | 0.028935 | 1970-01-02 01:50 | cp_activity_42
122 | unloading:barge_0 | barge_0 | 1970-01-02 01:42 | ACTIVE | 0.023148 | 1970-01-02 02:15 | cp_activity_95
123 | unloading:barge_0 | to_site | 1970-01-02 01:42 | ACTIVE | 0.023148 | 1970-01-02 02:15 | cp_activity_95
124 | sailing full:barge_1 | barge_1 | 1970-01-02 01:50 | ACTIVE | 0.023148 | 1970-01-02 02:23 | cp_activity_84
125 | basic activity:barge_0 | barge_0 | 1970-01-02 02:15 | ACTIVE | 0.023148 | 1970-01-02 02:48 | cp_activity_12
126 | unloading:barge_1 | barge_1 | 1970-01-02 02:23 | ACTIVE | 0.023148 | 1970-01-02 02:57 | cp_activity_105
127 | unloading:barge_1 | to_site | 1970-01-02 02:23 | ACTIVE | 0.023148 | 1970-01-02 02:57 | cp_activity_105
128 | sailing empty:barge_0 | barge_0 | 1970-01-02 02:48 | ACTIVE | 0.023148 | 1970-01-02 03:22 | cp_activity_54
129 | basic activity:barge_1 | barge_1 | 1970-01-02 02:57 | ACTIVE | 0.023148 | 1970-01-02 03:30 | cp_activity_22
130 | loading:barge_0 | from_site | 1970-01-02 03:22 | ACTIVE | 0.028935 | 1970-01-02 04:03 | cp_activity_33
131 | loading:barge_0 | barge_0 | 1970-01-02 03:22 | ACTIVE | 0.028935 | 1970-01-02 04:03 | cp_activity_33
132 | sailing empty:barge_1 | barge_1 | 1970-01-02 03:30 | ACTIVE | 0.023148 | 1970-01-02 04:03 | cp_activity_64
133 | loading:barge_1 | from_site | 1970-01-02 04:03 | ACTIVE | 0.028935 | 1970-01-02 04:45 | cp_activity_43
134 | sailing full:barge_0 | barge_0 | 1970-01-02 04:03 | ACTIVE | 0.023148 | 1970-01-02 04:37 | cp_activity_75
135 | loading:barge_1 | barge_1 | 1970-01-02 04:03 | ACTIVE | 0.028935 | 1970-01-02 04:45 | cp_activity_43
136 | unloading:barge_0 | to_site | 1970-01-02 04:37 | ACTIVE | 0.023148 | 1970-01-02 05:10 | cp_activity_96
137 | unloading:barge_0 | barge_0 | 1970-01-02 04:37 | ACTIVE | 0.023148 | 1970-01-02 05:10 | cp_activity_96
138 | sailing full:barge_1 | barge_1 | 1970-01-02 04:45 | ACTIVE | 0.023148 | 1970-01-02 05:18 | cp_activity_85
139 | unloading:barge_1 | to_site | 1970-01-02 05:18 | ACTIVE | 0.023148 | 1970-01-02 05:52 | cp_activity_106
140 | unloading:barge_1 | barge_1 | 1970-01-02 05:18 | ACTIVE | 0.023148 | 1970-01-02 05:52 | cp_activity_106
141 | basic activity vessel_last | vessel_last | 1970-01-02 05:52 | ACTIVE | 0.0011574 | 1970-01-02 05:53 | cp_activity_2
142 | sailing empty: vessel_last | vessel_last | 1970-01-02 05:53 | ACTIVE | 0.0011574 | 1970-01-02 05:55 | cp_activity_44
143 | loading vessel_last | from_site | 1970-01-02 05:55 | ACTIVE | 0.028935 | 1970-01-02 06:37 | cp_activity_23
144 | loading vessel_last | vessel_last | 1970-01-02 05:55 | ACTIVE | 0.028935 | 1970-01-02 06:37 | cp_activity_23
145 | sailing full vessel_last | vessel_last | 1970-01-02 06:37 | ACTIVE | 0.0011574 | 1970-01-02 06:38 | cp_activity_65
146 | unloading vessel_last | to_site2 | 1970-01-02 06:38 | ACTIVE | 0.0011574 | 1970-01-02 06:40 | cp_activity_86
147 | unloading vessel_last | vessel_last | 1970-01-02 06:38 | ACTIVE | 0.0011574 | 1970-01-02 06:40 | cp_activity_86