## Sheet1
| vessel | activity_name | activity_type | location | dredge_area | avg_duration | avg_displaced | avg_prodcution | tot_duration | tot_displaced | nr_days
0 | wid1 | activity_001 | day_work | A | A | 0.48 | 144.44 | 300 | 4.33 | 1300 | 9
1 | wid1 | activity_001 | day_work | D | D | 11.26 | 3377.78 | 300 | 101.33 | 30400 | 9
2 | wid1 | activity_001 | increased_night_work | D | D | 5.33 | 1066.67 | 200 | 48 | 9600 | 9
3 | wid1 | activity_001 | initial_mob | D | D | 0.13 | 0 | 0 | 1.17 | 0 | 9
4 | wid1 | activity_001 | night_demob | A | A | 1.17 | 0 | 0 | 10.5 | 0 | 9
5 | wid1 | activity_001 | night_mob | A | A | 1.17 | 0 | 0 | 10.5 | 0 | 9
6 | wid1 | activity_001 | night_work | A | A | 4.46 | 669.44 | 150 | 40.17 | 6025 | 9
7 | wid1 | activity_002 | day_work | E | E | 11.92 | 3576.47 | 300 | 202.67 | 60800 | 17
8 | wid1 | activity_002 | increased_night_work | C | C | 0.35 | 70.59 | 200 | 6 | 1200 | 17
9 | wid1 | activity_002 | increased_night_work | E | E | 5.65 | 1129.41 | 200 | 96 | 19200 | 17
10 | wid1 | activity_002 | initial_mob | E | E | 0.06 | 0 | 0 | 1 | 0 | 17
11 | wid1 | activity_002 | night_demob | A | A | 0.66 | 0 | 0 | 11.25 | 0 | 17
12 | wid1 | activity_002 | night_demob | B | B | 0.48 | 0 | 0 | 8.17 | 0 | 17
13 | wid1 | activity_002 | night_demob | C | C | 0.06 | 0 | 0 | 1.08 | 0 | 17
14 | wid1 | activity_002 | night_mob | A | A | 0.66 | 0 | 0 | 11.25 | 0 | 17
15 | wid1 | activity_002 | night_mob | B | B | 0.48 | 0 | 0 | 8.17 | 0 | 17
16 | wid1 | activity_002 | night_mob | C | C | 0.06 | 0 | 0 | 1.08 | 0 | 17
17 | wid1 | activity_002 | night_work | A | A | 1.85 | 277.94 | 150 | 31.5 | 4725 | 17
18 | wid1 | activity_002 | night_work | B | B | 1.51 | 226.47 | 150 | 25.67 | 3850 | 17
19 | wid1 | activity_002 | night_work | C | C | 0.25 | 36.76 | 150 | 4.17 | 625 | 17
20 | wid1 | activity_003 | day_work | C | C | 1.03 | 308.65 | 300 | 53.5 | 16050 | 52
21 | wid1 | activity_003 | day_work | F | F | 6.41 | 1923.08 | 300 | 333.33 | 100000 | 52
22 | wid1 | activity_003 | day_work | L | L | 0.38 | 113.6 | 300 | 19.69 | 5907 | 52
23 | wid1 | activity_003 | day_work | M | M | 0.88 | 265.38 | 300 | 46 | 13800 | 52
24 | wid1 | activity_003 | day_work | N | N | 1.91 | 572.12 | 300 | 99.17 | 29750 | 52
25 | wid1 | activity_003 | delay | F | F | 0.52 | 0 | 0 | 26.85 | 0 | 52
26 | wid1 | activity_003 | increased_night_work | C | C | 1.17 | 233.17 | 200 | 60.62 | 12125 | 52
27 | wid1 | activity_003 | increased_night_work | L | L | 0.46 | 92.31 | 200 | 24 | 4800 | 52
28 | wid1 | activity_003 | increased_night_work | M | M | 1.5 | 300 | 200 | 78 | 15600 | 52
29 | wid1 | activity_003 | initial_mob | F | F | 0.05 | 0 | 0 | 2.42 | 0 | 52
30 | wid1 | activity_003 | initial_mob | N | N | 0.02 | 0 | 0 | 1 | 0 | 52
31 | wid1 | activity_003 | night_demob | C | C | 0.2 | 0 | 0 | 10.5 | 0 | 52
32 | wid1 | activity_003 | night_demob | L | L | 0.08 | 0 | 0 | 4.25 | 0 | 52
33 | wid1 | activity_003 | night_demob | M | M | 0.32 | 0 | 0 | 16.5 | 0 | 52
34 | wid1 | activity_003 | night_demob | N | N | 0.61 | 0 | 0 | 31.67 | 0 | 52
35 | wid1 | activity_003 | night_mob | C | C | 0.2 | 0 | 0 | 10.5 | 0 | 52
36 | wid1 | activity_003 | night_mob | L | L | 0.11 | 0 | 0 | 5.67 | 0 | 52
37 | wid1 | activity_003 | night_mob | M | M | 0.35 | 0 | 0 | 18 | 0 | 52
38 | wid1 | activity_003 | night_mob | N | N | 0.58 | 0 | 0 | 30.08 | 0 | 52
39 | wid1 | activity_003 | night_work | C | C | 0.97 | 146.15 | 150 | 50.67 | 7600 | 52
40 | wid1 | activity_003 | night_work | L | L | 0.38 | 56.94 | 149.92 | 19.75 | 2961 | 52
41 | wid1 | activity_003 | night_work | M | M | 1.18 | 177.4 | 150 | 61.5 | 9225 | 52
42 | wid1 | activity_003 | night_work | N | N | 4.7 | 704.62 | 149.96 | 244.33 | 36640 | 52
43 | wid1 | activity_004 | day_work | G | G | 6.67 | 2000 | 300 | 166.67 | 50000 | 25
44 | wid1 | activity_004 | day_work | N | N | 3.97 | 1192 | 300 | 99.33 | 29800 | 25
45 | wid1 | activity_004 | initial_mob | G | G | 0.04 | 0 | 0 | 1 | 0 | 25
46 | wid1 | activity_004 | night_demob | N | N | 1.32 | 0 | 0 | 33 | 0 | 25
47 | wid1 | activity_004 | night_mob | N | N | 1.32 | 0 | 0 | 33 | 0 | 25
48 | wid1 | activity_004 | night_work | N | N | 10.68 | 1602 | 150 | 267 | 40050 | 25
49 | wid1 | activity_005 | day_work | H | H | 6.44 | 1932.69 | 300 | 335 | 100500 | 52
50 | wid1 | activity_005 | day_work | N | N | 4.34 | 1301.92 | 300 | 225.67 | 67700 | 52
51 | wid1 | activity_005 | initial_mob | H | H | 0.02 | 0 | 0 | 1 | 0 | 52
52 | wid1 | activity_005 | night_demob | N | N | 1.2 | 0 | 0 | 62.33 | 0 | 52
53 | wid1 | activity_005 | night_mob | N | N | 1.2 | 0 | 0 | 62.33 | 0 | 52
54 | wid1 | activity_005 | night_work | N | N | 10.8 | 1619.77 | 149.96 | 561.67 | 84228 | 52
55 | wid1 | activity_010 | day_work | N | N | 11.88 | 3564.58 | 300 | 142.58 | 42775 | 12
56 | wid1 | activity_010 | initial_mob | N | N | 0.12 | 0 | 0 | 1.42 | 0 | 12
57 | wid1 | activity_010 | night_work | N | N | 12 | 1800 | 150 | 144 | 21600 | 12
58 | wid1 | activity_011 | day_work | O | O | 11.99 | 3598.37 | 300 | 2207 | 662100 | 184
59 | wid1 | activity_011 | initial_mob | O | O | 0.01 | 0 | 0 | 1 | 0 | 184
60 | wid1 | activity_011 | night_work | O | O | 12 | 1800 | 150 | 2208 | 331200 | 184
61 | wid1 | activity_013 | day_work | I | I | 6.54 | 1961.36 | 300 | 503.42 | 151025 | 77
62 | wid1 | activity_013 | day_work | O | O | 0.1 | 30.19 | 300 | 7.75 | 2325 | 77
63 | wid1 | activity_013 | day_work | P | P | 4.06 | 1218.18 | 300 | 312.67 | 93800 | 77
64 | wid1 | activity_013 | delay | I | I | 0.07 | 0 | 0 | 5.15 | 0 | 77
65 | wid1 | activity_013 | initial_mob | I | I | 0.02 | 0 | 0 | 1.42 | 0 | 77
66 | wid1 | activity_013 | night_demob | O | O | 0.06 | 0 | 0 | 4.25 | 0 | 77
67 | wid1 | activity_013 | night_demob | P | P | 1.23 | 0 | 0 | 94.5 | 0 | 77
68 | wid1 | activity_013 | night_mob | O | O | 0.06 | 0 | 0 | 4.25 | 0 | 77
69 | wid1 | activity_013 | night_mob | P | P | 1.23 | 0 | 0 | 94.5 | 0 | 77
70 | wid1 | activity_013 | night_work | O | O | 0.35 | 51.81 | 149.96 | 26.6 | 3989 | 77
71 | wid1 | activity_013 | night_work | P | P | 10.31 | 1545.78 | 150 | 793.5 | 119025 | 77
72 | wid1 | activity_014 | day_work | J | J | 11.95 | 3585 | 300 | 239 | 71700 | 20
73 | wid1 | activity_014 | increased_night_work | J | J | 6 | 1200 | 200 | 120 | 24000 | 20
74 | wid1 | activity_014 | initial_mob | J | J | 0.05 | 0 | 0 | 1 | 0 | 20
75 | wid1 | activity_014 | night_demob | P | P | 1.42 | 0 | 0 | 28.33 | 0 | 20
76 | wid1 | activity_014 | night_mob | P | P | 1.42 | 0 | 0 | 28.33 | 0 | 20
77 | wid1 | activity_014 | night_work | P | P | 3.17 | 475 | 150 | 63.33 | 9500 | 20
78 | wid1 | activity_015 | day_work | K | K | 11.59 | 3476.47 | 300 | 197 | 59100 | 17
79 | wid1 | activity_015 | day_work | P | P | 0.27 | 82.35 | 300 | 4.67 | 1400 | 17
80 | wid1 | activity_015 | increased_night_work | K | K | 5.65 | 1129.41 | 200 | 96 | 19200 | 17
81 | wid1 | activity_015 | initial_mob | K | K | 0.06 | 0 | 0 | 1 | 0 | 17
82 | wid1 | activity_015 | night_demob | P | P | 1.33 | 0 | 0 | 22.67 | 0 | 17
83 | wid1 | activity_015 | night_mob | P | P | 1.33 | 0 | 0 | 22.67 | 0 | 17
84 | wid1 | activity_015 | night_work | P | P | 3.76 | 564.71 | 150 | 64 | 9600 | 17
85 | wid1 | activity_020 | day_work | P | P | 11.95 | 3584.62 | 300 | 310.67 | 93200 | 26
86 | wid1 | activity_020 | initial_mob | P | P | 0.05 | 0 | 0 | 1.33 | 0 | 26
87 | wid1 | activity_020 | night_work | P | P | 12 | 1800 | 150 | 312 | 46800 | 26
88 | wid2 | activity_021 | day_work | H | H | 6.53 | 1959.62 | 300 | 1019 | 305700 | 156
89 | wid2 | activity_021 | day_work | L | L | 1.17 | 351.92 | 300 | 183 | 54900 | 156
90 | wid2 | activity_021 | day_work | M | M | 0.35 | 104.33 | 300 | 54.25 | 16275 | 156
91 | wid2 | activity_021 | day_work | N | N | 2.72 | 816.03 | 300 | 424.33 | 127300 | 156
92 | wid2 | activity_021 | delay | H | H | 0.11 | 0 | 0 | 17.75 | 0 | 156
93 | wid2 | activity_021 | increased_night_work | L | L | 1.62 | 323.08 | 200 | 252 | 50400 | 156
94 | wid2 | activity_021 | increased_night_work | M | M | 0.5 | 100 | 200 | 78 | 15600 | 156
95 | wid2 | activity_021 | initial_mob | H | H | 0.02 | 0 | 0 | 2.83 | 0 | 156
96 | wid2 | activity_021 | night_demob | L | L | 0.29 | 0 | 0 | 45 | 0 | 156
97 | wid2 | activity_021 | night_demob | M | M | 0.09 | 0 | 0 | 14.67 | 0 | 156
98 | wid2 | activity_021 | night_demob | N | N | 0.78 | 0 | 0 | 121.83 | 0 | 156
99 | wid2 | activity_021 | night_mob | L | L | 0.29 | 0 | 0 | 45 | 0 | 156
100 | wid2 | activity_021 | night_mob | M | M | 0.1 | 0 | 0 | 16 | 0 | 156
101 | wid2 | activity_021 | night_mob | N | N | 0.78 | 0 | 0 | 121.83 | 0 | 156
102 | wid2 | activity_021 | night_work | L | L | 1.33 | 198.92 | 149.91 | 207 | 31032 | 156
103 | wid2 | activity_021 | night_work | M | M | 0.41 | 60.9 | 150 | 63.33 | 9500 | 156
104 | wid2 | activity_021 | night_work | N | N | 6.91 | 1036.42 | 149.96 | 1078.17 | 161682 | 156
105 | wid2 | activity_024 | day_work | N | N | 11.87 | 3561.36 | 300 | 130.58 | 39175 | 11
106 | wid2 | activity_024 | delay | N | N | 0.3 | 0 | 0 | 3.33 | 0 | 11
107 | wid2 | activity_024 | initial_mob | N | N | 0.13 | 0 | 0 | 1.42 | 0 | 11
108 | wid2 | activity_024 | night_work | N | N | 11.7 | 1754.55 | 150 | 128.67 | 19300 | 11
109 | wid2 | activity_025 | day_work | O | O | 11.99 | 3598.37 | 300 | 2207 | 662100 | 184
110 | wid2 | activity_025 | initial_mob | O | O | 0.01 | 0 | 0 | 1 | 0 | 184
111 | wid2 | activity_025 | night_work | O | O | 12 | 1800 | 150 | 2208 | 331200 | 184
112 | wid2 | activity_027 | day_work | I | I | 6.53 | 1960.2 | 300 | 496.58 | 148975 | 76
113 | wid2 | activity_027 | day_work | O | O | 0.1 | 30.59 | 300 | 7.75 | 2325 | 76
114 | wid2 | activity_027 | day_work | P | P | 4.07 | 1219.74 | 300 | 309 | 92700 | 76
115 | wid2 | activity_027 | initial_mob | I | I | 0.02 | 0 | 0 | 1.42 | 0 | 76
116 | wid2 | activity_027 | night_demob | O | O | 0.06 | 0 | 0 | 4.25 | 0 | 76
117 | wid2 | activity_027 | night_demob | P | P | 1.22 | 0 | 0 | 93 | 0 | 76
118 | wid2 | activity_027 | night_mob | O | O | 0.06 | 0 | 0 | 4.25 | 0 | 76
119 | wid2 | activity_027 | night_mob | P | P | 1.22 | 0 | 0 | 93 | 0 | 76
120 | wid2 | activity_027 | night_work | O | O | 0.42 | 62.64 | 149.95 | 31.75 | 4761 | 76
121 | wid2 | activity_027 | night_work | P | P | 10.3 | 1545.39 | 150 | 783 | 117450 | 76
122 | wid2 | activity_028 | day_work | J | J | 11.95 | 3586.36 | 300 | 263 | 78900 | 22
123 | wid2 | activity_028 | increased_night_work | J | J | 5.77 | 1154.55 | 200 | 127 | 25400 | 22
124 | wid2 | activity_028 | initial_mob | J | J | 0.05 | 0 | 0 | 1 | 0 | 22
125 | wid2 | activity_028 | night_demob | P | P | 1.42 | 0 | 0 | 31.17 | 0 | 22
126 | wid2 | activity_028 | night_mob | P | P | 1.42 | 0 | 0 | 31.17 | 0 | 22
127 | wid2 | activity_028 | night_work | P | P | 3.39 | 509.09 | 150 | 74.67 | 11200 | 22
128 | wid2 | activity_029 | day_work | K | K | 11.93 | 3580 | 300 | 179 | 53700 | 15
129 | wid2 | activity_029 | increased_night_work | K | K | 6 | 1200 | 200 | 90 | 18000 | 15
130 | wid2 | activity_029 | initial_mob | K | K | 0.07 | 0 | 0 | 1 | 0 | 15
131 | wid2 | activity_029 | night_demob | P | P | 1.33 | 0 | 0 | 20 | 0 | 15
132 | wid2 | activity_029 | night_mob | P | P | 1.33 | 0 | 0 | 20 | 0 | 15
133 | wid2 | activity_029 | night_work | P | P | 3.33 | 500 | 150 | 50 | 7500 | 15
134 | wid2 | activity_034 | day_work | P | P | 11.74 | 3522.32 | 300 | 328.75 | 98625 | 28
135 | wid2 | activity_034 | delay | P | P | 0.64 | 0 | 0 | 17.92 | 0 | 28
136 | wid2 | activity_034 | initial_mob | P | P | 0.05 | 0 | 0 | 1.33 | 0 | 28
137 | wid2 | activity_034 | night_work | P | P | 11.57 | 1735.71 | 150 | 324 | 48600 | 28
138 | hopper1 | activity_035 | day_work | A | A | 12 | 4200 | 350 | 216 | 75600 | 18
139 | hopper1 | activity_035 | delay | A | A | 0.52 | 0 | 0 | 9.29 | 0 | 18
140 | hopper1 | activity_035 | night_work | A | A | 11.48 | 4019.44 | 350 | 206.71 | 72350 | 18
141 | hopper1 | activity_036 | day_work | B | B | 12 | 4200 | 350 | 84 | 29400 | 7
142 | hopper1 | activity_036 | delay | B | B | 1.08 | 0 | 0 | 7.57 | 0 | 7
143 | hopper1 | activity_036 | night_work | B | B | 10.92 | 3821.43 | 350 | 76.43 | 26750 | 7
144 | hopper1 | activity_037 | day_work | C | C | 12 | 4200 | 350 | 132 | 46200 | 11
145 | hopper1 | activity_037 | night_work | C | C | 12 | 4200 | 350 | 132 | 46200 | 11
146 | hopper1 | activity_038 | day_work | H | H | 6.54 | 2287.8 | 350 | 268 | 93800 | 41
147 | hopper1 | activity_038 | day_work | P | P | 5.46 | 1912.2 | 350 | 224 | 78400 | 41
148 | hopper1 | activity_038 | night_work | P | P | 12 | 4200 | 350 | 492 | 172200 | 41